## Checklist (hidden)
Assigned | Tasks | Status
Event managers: | 1st meeting with the planning team | TRUE
Prof. Yahya Al Wahaib | determine overall budget for the event | TRUE
Dr. Hamed AlHajri | oversees the overall planning and management of the conference | TRUE
Dr. Waled AL Harthi
Dr. Mohammed Al Saqri
Dr. Francisco Dumanig
Assigned | Tasks
Registration Committee | 1. prepares conference registration | TRUE
Dr. Francisco Dumanig | 2. establishes delegate payment policy | TRUE
Aries Dahan Gan | 3. creates and updates registration forms | FALSE
Ahmed Al Sharqawy | 4. handles online and onsite registration | FALSE
| 5. acknowledges registration and sends the confirmation to participants | FALSE
| 6. prepares and updates the lists of confirmed participants | FALSE
| 7. records each receipt in a computer file | FALSE
| 8. sends program to presenters and participants | FALSE
FALSE
Assigned | Tasks
Abstract Review Committee | sets qualifications for reviewers; | TRUE
Dr. Francisco Dumanig | reviews and revises abstract guidelines | TRUE
University of Hawaí'i Staff | assigns abstracts for reviews; | TRUE
| evaluates abstract reviews; makes final decisions on abstract acceptances | TRUE
| oversees the review process to ensure the relevance and quality of the presentations | TRUE
| categorizes abstracts into different categories (per sessions) | TRUE
Assigned | Tasks
Marketing/Production Committee | brands the event with conference logo | TRUE
Noof Al Saidi | creates promotional plan - Internet campaign, printed materials, video trailer of the event | TRUE
Dhekra Abdullah Ali Al Mardi | designs and prints brochures, tickets, advertising materials, invitations | FALSE
Moza Mohammed Al Hindasi | publicizes the call for abstracts | TRUE
Mohammed Salim Al Maskar | designs, plans & prepares conference kits name tags, presents etc | FALSE
Dr. Francisco Dumanig | Posts the event to conference announcement sites | TRUE
University of Hawaí'i Staff | creates and prepares certificates of the attendees, participants, plenary and guest speakers | FALSE
Assigned | Tasks
Digital/Technical Committee | checks and sets up technical requirements e.g. lighting, camera, audio, connectivity, etc. | FALSE
Mohammed Salim Al Maskar | documents the event (video and photo) | FALSE
Noof Al Saidi | Takes charge to the creation of T-Card, Keynote and Plenary AVPs | FALSE
Assigned | Tasks
Communications Committee | communicates/invites speakers | TRUE
Dr. Waleed Al Harthy | ensures endorsement letter from MOHERI | TRUE
Dalal Al Musalami | invites/communicates with other HEIs and university partners locally, nationally, and internationally | TRUE
Dr. Francisco Dumanig | obtains biographical information from the invited speakers | TRUE
Aries Dahan Gan | maintains communication with invited speakers to confirm the date and time for their presentations, flight details, accommodation and transportation | TRUE
TRUE
Assigned | Tasks
Finance/Budget Committee | determines the overall budget | TRUE
Dr. Hamed AlHajri | monitors cash flow | TRUE
Mr. Ali Al Manji | records expenses and income | TRUE
Prof. Yahya Al Wahaib | creates ongoing financial reports and updates | TRUE
Dr. Waleed Al Harthy | compiles final report | FALSE
| verifies payments | TRUE
| prepares liquidation report | FALSE
| identifies potential sponsors | TRUE
| negotiates contracts with sponsors | TRUE
Assigned | Tasks
Food & Venue Committee | books venue & equipment to be used | TRUE
| plans food and beverage needs | FALSE
| coordinates with the planning committee | FALSE
| coordinates with the TECHNICAL COMMITTEE on audio/visual needs | FALSE
| designs/decorates main hall | FALSE
| ensures sitting arrangements | FALSE
Assigned | Tasks
Transportation & Accommodation Committee | coordinates with Planning Team and Event Manager | FALSE
Yousuf ALMaskri | liaises with hotels | FALSE
| selects and books hotel accommodation for invited speakers | FALSE
| ensures transportation for the invited speakers | FALSE
| verifies pickup times and location of Guests | FALSE
FALSE
Assigned | Tasks
Program Committee | designs program flow | TRUE
Salim Shamakhi | identifies/appoints MC | TRUE
Noof Al Saidi | identifies/appoints session chairs & timers | TRUE
Aries Dahan Gan | sets guidelines for presentation | TRUE
Maxine Rodiguez | coordinates with speakers/presenters | TRUE
| ensures presentation materials and equipment | FALSE
| establishes onsite audio/visual and IT needs (coordinates with the Technical Committee) | FALSE
| Schedules Technical Dry Run of the event | FALSE
| Schedules & coordinates performers (dancers, musicians, or singers) for the event | FALSE
| Make arrangements for VIPs, including special seating, security, and exclusive interactions. | FALSE
| Coordinate protocol procedures with government or official representatives if necessary. | FALSE
Assigned | Tasks
Safety Committee | ensures safety protocols: | FALSE
Hamed Al Barwani

## Committees and Tasks
Registration Committee: Dr. Hameed and Fatema Al Hakamani | Completion Date | Status
1. prepares conference registration |  | FALSE | In Progress
2. creates and updates registration forms (coordinate with Ms. Iman) |  | FALSE | In Progress
3. handles online and onsite registration |  | FALSE | In Progress
4. acknowledges registration and sends the confirmation to participants |  | FALSE | In Progress
5. prepares and updates the lists of confirmed participants |  | FALSE | In Progress
6. records each receipt in a computer file |  | FALSE | In Progress
7. sends program to presenters and participants |  | FALSE | In Progress
Marketing/Production Committee: Ima Al Butaini and Abdullah Al Maawali
brands the event with symposium logo |  | TRUE | Completed
creates promotional plan - Internet campaign, printed materials, video trailer of the event |  | FALSE | In Progress
designs and prints brochures, tickets, advertising materials, invitations |  | FALSE | In Progress
designs, plans & prepares conference kits name tags, presents etc |  | FALSE | In Progress
Posts the event updates |  | FALSE | In Progress
Creates and designs certificates of the attendees, participants, plenary and guest speakers |  | FALSE | In Progress
Video Production: Abdullah Al Maawali
checks and sets up technical requirements e.g. lighting, camera, audio, connectivity, etc. |  | FALSE | In Progress
documents the event (video and photo) |  | FALSE | In Progress
Takes charge to the creation of T-Card, Keynote and Plenary AVPs |  | FALSE | In Progress
Communications Committee: Maxine Rodriguez and Ashraf Tantish
communicates/invites speakers |  | FALSE | In Progress
ensures endorsement letter from MOHERI |  | FALSE | In Progress
invites/communicates with other HEIs and university partners locally, nationally, and internationally |  | FALSE | In Progress
obtains biographical information from the invited speakers |  | FALSE | In Progress
maintains communication with invited speakers to confirm the date and time for their presentations, flight details, accommodation and transportation |  | FALSE | In Progress
Finance/Budget Committee: Dr. Waleed and Aries
determines the overall budget |  | FALSE | In Progress
monitors cash flow |  | FALSE | In Progress
records expenses and income |  | FALSE | In Progress
creates ongoing financial reports and updates |  | FALSE | In Progress
compiles final report |  | FALSE | In Progress
prepares liquidation report |  | FALSE | In Progress
identifies potential sponsors |  | FALSE | In Progress
Food & Venue Committee: Aries - SALIM AL SHAMAKHI
books venue & equipment to be used |  | FALSE | In Progress
plans food and beverage needs |  | FALSE | In Progress
coordinates with the planning committee |  | FALSE | In Progress
coordinates with the TECHNICAL COMMITTEE on audio/visual needs |  | FALSE | In Progress
designs/decorates main hall |  | FALSE | In Progress
ensures sitting arrangements |  | FALSE | In Progress
Transportation & Accommodation Committee: Aries - SALIM AL SHAMAKHI
coordinates with Planning Team and Event Manager |  | FALSE | In Progress
liaises with hotels |  | FALSE | In Progress
selects and books hotel accommodation for invited speakers |  | FALSE | In Progress
ensures transportation for the invited speakers |  | FALSE | In Progress
verifies pickup times and location of Guests |  | FALSE | In Progress
|  | FALSE | In Progress
Program Committee: Maxine Rodriguez and Ashraf Tantish
designs program flow |  | FALSE | In Progress
identifies/appoints MC |  | FALSE | In Progress
coordinates with speakers/presenters |  | FALSE | In Progress
ensures presentation materials and equipment |  | FALSE | In Progress
establishes onsite audio/visual and IT needs (coordinates with the Technical Committee) |  | FALSE | In Progress
Schedules Technical Dry Run of the event |  | FALSE | In Progress
Make arrangements for VIPs, including special seating, security, and exclusive interactions. |  | FALSE | In Progress
Safety Committee: Aries - SALIM AL SHAMAKHI
ensures safety protocols: |  | FALSE | In Progress

## Speaker 1 Details
Dr. Junifer Abatayo is a Fellow of the Higher Education Academy (now Advance HE, UK). He finished his Postgraduate Studies in Teaching in Higher Education (PGTHE) at Edge Hill University, Liverpool, UK. | University of Bahrain Faculty Info: https://teachers.uob.edu.bh/faculty/faculty-profile/?faculty=2380 | ORCID Connecting research and researcher https://orcid.org/0000-0001-9306-4131
He also finished his Doctor of Education, Master of Arts (English), and Bachelor in Secondary Education (English) from the Misamis University, the Philippines. | Research Gate Account https://www.researchgate.net/profile/Junifer-Abatayo-2
Currently, he is teaching at the English Language Department of Bahrain Teachers College, University of Bahrain.
Apart from his teaching roles, Dr. Abatayo is the Middle East Regional Representative of the Asian Association for Language Assessment (AALA).
He is also a trained Site Reviewer for the Commission on English Language Program Accreditation (CEA), USA, and Oman Academic Accreditation Authority (OAAA, Oman).
His research interests include TESOL, Testing and Assessment, Communities of Good Practice, and Teaching and Learning in Higher Education.
Dr. Abatayo is the founding chair of TESOL Oman Sohar, and Kingdom of Saudi Arabia Association of Language Teachers (KSAALT TESOL) Yanbu Chapter.